# District & Church Management System Initiative - Executive Summary (v1.2)

v1.2 Change Note: Per Executive Sponsor direction (Feb 10, 2026), Phase 2 (ChurchCM local church front-end) has been descoped from active planning and moved to a future consideration. This version refocuses on Phase 1 as a District office initiative and builds out a detailed task timeline for Phase 1-A and 1-B deliverables.

## Purpose

To build a reliable District office data repository and reporting foundation using ChMeetings — starting with the pastors’ directory and the online annual report — that supports accurate, consistent District-level oversight and planning.

## Problem Statement

- The District needs reliable data for annual reporting, planning, and oversight. Local churches don’t report well because they don’t track the data needed for “form-filling” with year-round operational discipline, using a system for its data (membership list and status, spiritual milestones, church attendance, group rosters, giving categories, etc.)

- Churches vary widely in size and technical capacity. Most don’t use a Church Management System (ChMS).

- Those who use a ChMS, use a variety of products (Planning Center, Breeze, Tithe.ly, ChurchTrac, Servant Keeper, etc.) with no District support.

- A full-featured, multi-tenant system (e.g., ChMeetings Diocese version) can be too complex for many small churches, leading to uneven adoption.

- C&MA CMS remains the required compliance system; our goal is to align District-critical identifiers and naming conventions between CMS and ChMeetings.

## Proposed Solution (Phase 1 Only — Active Scope)

1-A. Institutionalize ChMeetings as District Operational Backbone and System of Record

- Centralized Annual District reports from the churches (piloted for 2024 already)

- Official list of Pastors and workers in the Vietnamese District (piloted in 2023; directory framework shared Feb 2026)

- Official list of official churches and organizations in the District (needed in 2025)

- Collection of other participants in the District at multi-church events such as VAY Sports Fest, camp, conference, etc. (operational in 2025)

- Support the autonomy of any District local church’s operation on the platform (RP is operational in 2024)

- Jacksonville ChMeetings pilot — Chi Liêu working with MS Phát Mạnh Lê; learnings to inform future broader adoption strategy

1-B. Improving ChMeetings for Sustainability

- Review and define the District’s reporting template (minimum data elements and practices)

- Time-boxed Data Normalization Sprint for District-critical records (pastors / workers / delegates + official church names across C&MA and District systems)

- Standardize key data elements and conventions (people names, titles, roles)

- Provide a “Sample Church” configuration as a proof-of-concept and training environment

- Pilot with other willing churches in the District (Midway, Jacksonville)

- Organize a stakeholder community to charter the long-term District data governance

## Phase 1 Detailed Task Timeline

Stream A — Pastors’ Directory & Profiles

Owner: Pastor Peter Đoàn | Platform: ChMeetings

| Task | Description | Target |
| --- | --- | --- |
| A1. Audit current data | Review existing pastor/worker records in ChMeetings; identify gaps, duplicates, and naming inconsistencies | Feb 28, 2026 |
| A2. Define data standards | Agree on naming conventions, titles, roles, and required fields for pastor/worker profiles | Feb 28, 2026 |
| A3. Data normalization sprint | Clean and standardize all existing pastor/worker records to agreed conventions | Mar 31, 2026 |
| A4. Official church list | Establish and normalize the official list of churches and organizations in the District | Mar 31, 2026 |
| A5. Review & sign-off | Pastor Peter presents completed directory to Executive Sponsor for approval | Apr 15, 2026 |
| A6. Ongoing maintenance process | Document the process for keeping the directory current (new pastors, role changes, departures) | Apr 30, 2026 |

Stream B — Online Annual Report

Owner: Pastor Peter Đoàn + Pastor Bumble Hồ | Platform: ChMeetings

| Task | Description | Target |
| --- | --- | --- |
| B1. Review prior year report | Analyze the 2024 annual report template; identify minimum required data elements | Feb 28, 2026 |
| B2. Define reporting template | Draft the ChMeetings-based reporting template with minimum data fields; align with C&MA CMS requirements | Mar 15, 2026 |
| B3. Configure ChMeetings | Set up the reporting structure, forms, and workflows in ChMeetings Diocese tenant | Mar 31, 2026 |
| B4. Sample Church setup | Create a “Sample Church” configuration in ChMeetings as a training and proof-of-concept environment | Apr 15, 2026 |
| B5. Pilot with Midway | Pastor Peter’s church (Midway) completes a test annual report submission through ChMeetings | Apr 30, 2026 |
| B6. Training materials | Produce simple guide for churches on how to submit their annual report through ChMeetings | May 31, 2026 |
| B7. First live annual report cycle | All reporting churches submit 2025 annual report through ChMeetings | Aug 31, 2026 |

Stream C — Jacksonville ChMeetings Pilot

Owner: Chi Liêu | Pilot Church: Jacksonville, FL (MS Phát Mạnh Lê)

| Task | Description | Target |
| --- | --- | --- |
| C1. Kickoff with MS Phát | Chi and MS Phát align on scope, goals, and timeline for ChMeetings adoption at Jacksonville | Feb 28, 2026 |
| C2. Chi’s timeline assessment | Chi shares a realistic implementation timeline for Jacksonville with the team | Feb 28, 2026 |
| C3. ChMeetings setup for Jacksonville | Configure Jacksonville’s church tenant in ChMeetings | TBD (per Chi’s timeline) |
| C4. Data entry & onboarding | Enter Jacksonville membership data; train MS Phát and key staff | TBD |
| C5. First annual report submission | Jacksonville submits annual report through ChMeetings | TBD |
| C6. Pilot debrief | Chi and MS Phát share learnings with District team; inform future adoption strategy | TBD |

## Governance & Ownership

- Executive Sponsor: Pastor Trường Xuân Hồ

- Product Owner: Pastor Bumble Hồ

- Data Steward & Timeline Owner: Pastor Peter Đoàn — District data standards, naming conventions, directory, and reporting

- Implementation Lead: Mr. Simon (Chi) Liêu — Jacksonville pilot

- Technical Reviewer: Mr. Thanh Dang, Ph.D. (attended GLA, currently a Meta system architect)

- District Operations: Cô Trang — office operations

- Pilot Church: Jacksonville, FL — MS Phát Mạnh Lê

District leadership retains strategic control and oversight.

## Open Action Items

| Owner | Action Item | Due |
| --- | --- | --- |
| Pastor Peter Đoàn | Provide a realistic timeline for directory and annual reporting delivery | End of Feb 2026 |
| Chi Liêu | After working with MS Phát, share assessment of a reasonable ChMeetings implementation timeline for Jacksonville | End of Feb 2026 |

## Budget (Phase 1 Estimate)

- Existing ChMeetings Diocese subscription covers Phase 1 operations

- Additional costs (if needed): data cleanup support, training materials

- No new budget line required at this stage; to be confirmed by Pastor Peter’s timeline

Risks & Mitigation (Phase 1)

| Risk | Mitigation |
| --- | --- |
| Data quality | Agree on minimum standards before normalization sprint; Pastor Peter owns sign-off |
| Timeline slippage | Pastor Peter to set and own a realistic timeline by end of Feb 2026 |
| Low church participation | Start with Midway and Jacksonville as pilots; lead by example |
| Naming convention conflicts (CMS vs. ChMeetings) | Data Steward Pastor Peter to align conventions across both systems |
| Key person dependency | Document all processes and configurations in this repository |

## Phase 2 — Future Consideration (Descoped)

The following phases were proposed in v1.1 but are not in active scope. They will be revisited after Phase 1 is stable and the Jacksonville pilot produces learnings.

2-A. Local Church Front End Integration Evaluation (ChurchCM)

- ChurchCM (developed by Simon Liêu) proposed as a lightweight, per-church front-end

- Data sync to District ChMeetings via secure API-key-based integration

- Pending: verification of ChurchCM repository access, licensing/provenance, and documentation

- Pilot proposed with Jacksonville church — deferred until after ChMeetings pilot completes

2-B. District-wide ChurchCM Adoption

- DEXCOM endorsement and budget decision required

- Operating model and hosting cost model (~$15–$30/month/church) to be defined

- No timeline set; pending Phase 2-A evaluation and DEXCOM decision

Decision Requested

(DEXCOM agenda item removed per Executive Sponsor, Feb 10, 2026. The following decisions remain open for future consideration.)

- Confirm governance roles (acknowledged by Executive Sponsor).

- Approve Phase 1 (A & B) operational timeline once Pastor Peter submits it.

- Approve budget envelope if additional resources are needed beyond existing ChMeetings subscription.

- Revisit Phase 2-A & 2-B after Jacksonville pilot learnings — timing TBD.

# District & Church Management System Initiative - Executive Summary (v1.1)

## Purpose

To provide churches within the District with a sustainable church management solution that improves local ministry operations while enabling accurate, consistent District-level reporting.

## Problem Statement

- The District needs reliable data for annual reporting, planning, and oversight. Local churches don’t report well because they don’t track the data needed for “form-filling” with year-round operational discipline, using a system for its data (membership list and status, spiritual milestones, church attendance, group rosters, giving categories, etc.)

- Churches vary widely in size and technical capacity. Most don’t use a Church Management System (ChMS).

- Those who use a ChMS, use a variety of products (Planning Center, Breeze, Tithe.ly, ChurchTrac, Servant Keeper, etc.) with no District support.

- A full-featured, multi-tenant system (e.g., ChMeetings Diocese version) can be too complex for many small churches, leading to uneven adoption.

- C&MA CMS remains the required compliance system; our goal is to align District-critical identifiers and naming conventions between CMS and ChMeetings.

## Proposed Solution (Phased Approach)

Use a phased approach at the District level and for the local churches.

### 1-A. Institutionalize ChMeetings for District Operational Backbone and System of Record

- Centralized Annual District reports from the churches (piloted for 2024 already)

- Official list of Pastors and workers in the  Vietnamese District (piloted in 2023)

- Official list of official churches and organizations in the District (needed in 2025)

- Collection of other participants in the District at multi-church events such as VAY Sports Fest, camp, conference, etc. (operational in 2025)

- Support the autonomy of any District local church’s operation on the platform (RP is operational in 2024)

### 1-B. Improving ChMeetings for Sustainability

- Review and define the District’s reporting template (minimum data elements and practices)

- Time-boxed Data Normalization Sprint for District-critical records ( pastors / workers / delegates + official church names across C&MA and District systems).

- Standardize key data elements and conventions (people names, titles, roles)

- Provide a “Sample Church” configuration as a proof-of-concept and training environment

- Pilot with other willing churches in the District (Midway, Jacksonville)

- Organize a stakeholder community to charter the long-term District data governance

### 2-A. Local Church Front End Integration Evaluation - (for local churches using ChurchCM)

- ChurchCM is proposed as an open-source, lightweight system developed by Simon Lieu (pending verification of repository access, licensing/provenance, and documentation).

- Any church could download, install, deployed it for their church by themselves, or through Simon Lieu’s support.

- ChurchCM focused on day-to-day ministry needs (Membership & guest tracking, Ministry groups, classes, events, Kids check-in, etc.)

- The data in the system can be submitted as the required Annual Report to the District’s ChMeetings using a Secure API-key-based sync. Only required metrics are shared.

- Pilot with Jacksonville church.

### 2-B. Local Church Front End Adoption for ChurchCM

- Once the open-sourced ChurchCM codebase is properly tested, it could be adopted widely for its:

  - Lower adoption barrier for small churches

  - Hides complexity while preserving capability

  - Supports long-term scalability and governance

  - Reduces technical and organizational risk, avoids vendor lock-in.

- DEXCOM will need to evaluate and approve:

  - Will it endorse the adoption of ChurchCM?

  - Will it subsidize the hosting of each local church running ChurchCM?  (~$15–$30/month/church)

  - What is the operating model for ChurchCM beyond having access to an open-sourced system that works well with the District data intake?

## Governance & Ownership

- Project Sponsor: Pastor Trường Xuân Hồ

- Product Owner: Pastor Bumble Hồ

- Lead Developer: Mr. Simon (Chi) Liêu

- Technical Reviewer: Mr. Thanh Dang, Ph.D. (attended GLA, currently a Meta system architect)

- Data Steward: Pastor Peter Đoàn, who works on District data standards and naming conventions

- Another District User: Cô Trang, who works on office operations

- Pilot Church for ChurchCM: Jacksonville, FL (Pastor Phát Mạnh Lê)

- Pilot Church for ChMeetings Diocese tenant: Midway, FL (Pastor Peter Doan)

District leadership retains strategic control and oversight.

## Timeline (High-Level)

- DEXCOM approval for Phase 1-A&B: Feb. 11, 2026

- DEXCOM approval for Phase 2-A integration pilot (reporting-first), with no rollout commitment: Mar. 1, 2026

- Pilot release: April 1, 2026

- Additional pilots: May 2026

- First official release: August 2026

- First District Annual Report for churches on the ChMeetings Diocese: 2027

- DEXCOM decision for Phase 2-B: Oct 1, 2026

- District rollout: Nov. 2026–Mar. 2027

- All churches operational with ChurchCM Integration: Dec 31, 2027

- First District Annual Report with ChurchCM Integration: 2028

## Budget (Initial Estimate)

- $2,000 (first year) for core infrastructure and tools

- $1,000/year starting second year

- Future: optional per-church hosting/support model (~$15–$30/month/church, if adopted)

## Risks & Mitigation

- Adoption risk: Start with pilots and lead by example (District churches); provide templates and training support.

- Data quality risk: Standardize minimum data elements and practices.

- Technical risk: Use modular design and open standards; keep integrations central and adoptions gated with DEXCOM approval as needed. API keys required for integrations.

- Sustainability risk: Clear ownership, documentation, and continuity plan for any custom components using GitHub open source repository.

## Decision Requested from DEXCOM

- Confirm governance roles.

- Approve Phase 1(A&B): ChMeetings as the District operational backbone, data-elements standardization, and authorize pilot deployment (Diocese model)

- Approve initial budget envelope (including training/pilot support, and data cleanup support if prioritized)

- Authorize Phase 2-A evaluation of an optional local front-end integration (e.g., ChurchCM) and pilot with the future decision of Phase 2-B on the horizon.